## Gantt Chart
Sea Horizon HBMS — Project Management Gantt Chart
Student: [Your Full Name] ¦ Module: BBIS133 PROJECT ¦ Deadline: 05 May 2026
Task / Milestone | Phase | Status | January |  | February |  | March |  | April |  |  |  | May
|  |  | Jan W3 20 Jan | Jan W4 27 Jan | Feb W1 3 Feb | Feb W2 10 Feb | Mar W1 3 Mar | Mar W2 10 Mar | Apr W1 7 Apr | Apr W2 14 Apr | Apr W3 21 Apr | Apr W4 28 Apr | May W1 5 May
Phase 1: Planning & System Foundation
Project idea conceptualisation | Phase 1 | ✔ Done
System scope & requirements defined | Phase 1 | ✔ Done
Database schema designed (high level) | Phase 1 | ✔ Done
Development environment setup (XAMPP) | Phase 1 | ✔ Done
Authentication approach planned (sessions) | Phase 1 | ✔ Done
★ Project Proposal submitted (26 Jan) | Milestone | ✔ Done | ★
Phase 2: Core System Implementation (Backend & Database)
MySQL database created (hbmsdb) | Phase 2 | ✔ Done
User registration & login (PDO prepared) | Phase 2 | ✔ Done
Admin login + session management | Phase 2 | ✔ Done
Room categories & facility management | Phase 2 | ✔ Done
Booking overlap detection algorithm | Phase 2 | ✔ Done
Booking approval / rejection workflow | Phase 2 | ✔ Done
★ Interim Report submitted (10 Feb) | Milestone | ✔ Done |  |  | ★
Phase 3: Frontend UI & User-Facing Pages
index.php — Landing page (luxury theme) | Phase 3 | ✔ Done
about.php — About hotel page | Phase 3 | ✔ Done
services.php + gallery.php pages | Phase 3 | ✔ Done
category-details.php — Room browsing | Phase 3 | ✔ Done
book-room.php — Booking form + cost calc | Phase 3 | ✔ Done
my-booking.php + view-application-detail | Phase 3 | ✔ Done
invoice.php — PDF invoice generation | Phase 3 | ✔ Done
contact.php — Enquiry submission form | Phase 3 | ✔ Done
Phase 4: Admin Dashboard & Advanced Features
dashboard.php — Stats overview panel | Phase 4 | ✔ Done
manage-category / add-category / edit-room | Phase 4 | ✔ Done
all-booking / approved / new / cancelled | Phase 4 | ✔ Done
Booking date-range reports (PDF/print) | Phase 4 | ✔ Done
Enquiry management (read/unread/view) | Phase 4 | ✔ Done
profile.php + change-password + forgot-password | Phase 4 | ✔ Done
Security audit (OWASP Top 10 check) | Phase 4 | ✔ Done
Manual testing of all features (UAT) | Phase 4 | ✔ Done
Phase 5: Documentation & Submission
Project-Proposal.html written | Phase 5 | ✔ Done
Interim-Report.html written | Phase 5 | ✔ Done
Final-Project-Report.html written | Phase 5 | ✔ Done
Gantt Chart management document | Phase 5 | ✔ Done
★ Final Report + Submission (5 May) | Milestone | ☐ Due | [10 empty] | ★
LEGEND
Phase 1 — Planning & System Foundation
Phase 2 — Core Backend & Database
Phase 3 — Frontend & User Pages
Phase 4 — Admin Dashboard & Testing
Phase 5 — Documentation & Submission
★ = Milestone